## Slide 1: Zekelman school
Notes: Hi, we are going to present a digital marketing campaign from a project management standpoint

## Slide 2: Group #12 : Team
Amit Sharma
0794488
Suhail Ahmed 0789949
Rajvi Mehta
0788372
Harshil Patel
0791261
Jayraj Radadiya
078
Notes: Our team members are Me, Kartik, Rajvi, Harshil and Farzin

## Slide 3: Introduction Company Problem Solution
DigitallyLearnt LLB., A newly founded digital educational content creator in the field of digital marketing, has developed products that have passed the quality examination and received optimal feedback from initial and limited launch.
Scale up the revenue and reaching more audiences is digitally promoting the product.
Sell more copies of its digital content to go further in the course of the growth and gain profits.
Running the first widespread digital marketing campaign for the current products .
This campaign will try to target potential customers on these popular platforms.
Aim to increase the exposure of the products' brands and convince new customers to purchase the product.
Notes: We are a digital content creator that produce online contents in the areas of digital business and commerce
One of our products has received good feedbacks and reviews from customers
so, we spotted a need to promote our product through digital marketing campaign which
will be the first widespread campaign of the company.
The objective is to attract potential customers to buy our product and enhance our company’s brand image

## Slide 4: Problem Statement: Company Problem Solution
DigitallyLearnt LLB., A newly founded digital educational content creator in the field of digital marketing, has developed products that have passed the quality examination and received optimal feedback from initial and limited launch.
Scale up the revenue and reaching more audiences is digitally promoting the product.
Sell more copies of its digital content to go further in the course of the growth and gain profits.
Running the first widespread digital marketing campaign for the current products .
This campaign will try to target potential customers on these popular platforms.
Aim to increase the exposure of the products' brands and convince new customers to purchase the product.
Notes: We are a digital content creator that produce online contents in the areas of digital business and commerce
One of our products has received good feedbacks and reviews from customers
so, we spotted a need to promote our product through digital marketing campaign which
will be the first widespread campaign of the company.
The objective is to attract potential customers to buy our product and enhance our company’s brand image

## Slide 5: Project Process Groups
Initiating
Planning
Executing
Monitoring & Controlling
Closing
Notes: In this presentation we will talk through different process groups from initiating and Closing of this project

## Slide 6: StakeHolders
Business Case
Project Charter
Stakeholder Register
Sponsor
Project Manager
Stake-holders
Deliverables
Recognition
In this phase we defined the Project, vision & overall scope and the business values from perspective of each stakeholder
Notes: Three documents needed for this group: Business case, project charter and Stakeholder register.
Our project’s Stakeholders include:
Marketing department, Software and development department, Customer care, customers, and higher management.
- We use Power & support grid and Interview stakeholders to determine the business values important to the stakeholders
The Business Values include Revenue and Brand value of the company and product
We use business value measures (KPI) to assess business value delivery.
Our main KPIs for this project are:
  Number of Impressions,
  Number of clicks,
  Number of purchases and the
  costs associated with each of these metrics
  (cost per impression, cost per click and Cost per acquisitions)
As it is an Internal Project:
We as Project Manger with the help of our Sponsor create our statement of work and then create Charter based on that
By having the Statement of work which is a description of the project (as we call it solution here )
& use the Benefit management plan (What is the benefits , when they will be realized , how they measured)
We combine those two documents as a comprehensive Business Case
& By considering our EEFs (As we mentioned before) & OPAs (financial data, other projects, some historical info ) our Project Charter has borened
Project Charter:
Project description & authorizing
Our commitment for the campaign
-
To create project charter we decide to use our Marketing consultant help & as UX team for some data gathering about the market preference then we Use some Meeting with different department to make our charter as logical as possible

## Slide 7: Data
Define Scope
Activities & Sequences
Deliverables
By using our initial documents and also considering our company’s OPA & EEFs, like Our Project life cycle and our Development approach (which is Agile in our case) we defined our project scope in detail.
Requirement Gathering
Project Requirement Gathering Method
Benchmarking,
Brainstorming
Interviews
User Stories
WBS
Notes: - Requirments are set of necessities & needs which are highlighted by stakeholders that we defined in our Stakeholder Registers in the previous part of the project
Here we also can create RTM (Requirement Traceability Matrix)
In our project most of the User stories for the project are provided by the Campaign manager ( which is one of the member of the team)
Our project was an Medium size project and requirments mostly collect by Project Manager & system Analysts
The work Break down and Activities are based on the PM’s knowledge area and Expert
Because we used agile methods we did not have Critical Path
We just use WBS and Activities sequences to predict a better estimates of our user stories in each sprint
Estimate Activity Duration
As we chose agile approach for our project , we use Planning poker method for estimating activity duration (in our case each user stories point)
Develop Schedule
Plan Cost management
Estimate Costs
Determine Budget
Plan Quality Management
Plan Resource Management
Estimate Activity Resource
Plan Communication Management
Plan Risk Management
Identify Risks
Perform Qualitative Risk Analysis
Perform Quantitative risk Analysis
Plan Risk Response
Plan Porcurment Management
Plan Stakeholder Engagement

## Slide 8: Methodology
Acceptable level of Quality
Quality Mgmt.
Resource Work Activity Chart
Resource Mgmt.
Org. Policies
Metrics
Hierarchical Chart
RACI Matrix
Communication Plan
Communication Mgmt.
Org. Policies
Dev. Approach
Notes: As we use agile approach, we use sprint retrospective with keeping KAIZEN (small changes) in mind of all team members we mention in the Project Communication document.
In Communication management we defined the channels and times and topics of project communication
For example we are going to use Slack to coordinate our activities and manage the communication flow
For Communication Mgmt. we’ve decided to:
Focus Internal Stakeholders we use Sprint Reviews
Focus on External Stakeholder like customers we utilize Customer Service department
Formal & Informal meetings are Based on Agile approach
There are no Scheduled official report, but there are short reports every week and also some charts like burn-down / burn up
Estimate Activity Resource
Using Team charter , Role & responsibilities
For our project it mostly limits to Human resources
Plan Risk Management
Identify Risks
Perform Qualitative Risk Analysis
Perform Quantitative risk Analysis
Plan Risk Response
Plan Porcurment Management
Plan Stakeholder Engagement

## Slide 9: Timeline
Notes: This RACI matrix is based on all the activities in the project that have been planned

## Slide 10: How we planned our project ...
Risk Register
Risk Mgmt.
Risk Response
Plan
Meeting & interviews
Root Cause Analysis
Stakeholder Engagement
Stakeholder Mgmt.
Expert Judgment
Meetings
Notes: Now is the time to Risk management. In our project:
Some risks that should be considered, for example:
  Overwhelming traffic may cause the website go down. The planned Response is to Create a medium (landing) page to manage incoming traffic
To Perform Qualitative Risk Analysis
- Because of the scope of the project is not big and not too complicated, it does not apply because it is time consuming & costly
In Our project the vendors are digital vendors with a worldwide standard and online contract so our Plan Procurement Management will be based on that.
Based on the interest of each stakeholders and their level & priority, we approached to them in many steps of the project.

## Slide 11: Progress
Direct & Manage Project Work
Change Request
Change Log
Project Management Plan
Project Milestones
Project Schedule
Risk Register
Requirement Gathering
Project Communication
…
Change Request
Change log
Lesson Learned Register
Manage Knowledge
Lesson Learned Register
Deliverables
Notes: Directing and managing work is one of the main process in this process group that directly affects the main deliverables of the project.
One of the changes that was requested, was to extend the time and resources needed to create campaign assets and contents because the initial estimation underestimated the necessary resources to create these assets.
This requested change is evaluated and accepted by the change board and subsequently had its impact on the related documents such as Schedules and WBS, and Cost, requirement gathering etc.
Deliverable examples in this project are:
Test campaign contents
UX design of landing page
Final landing page
All these are based on meetings and judgment.
Experts helps and using any change (Change log) & project schedules , Risk register and so on
We Manage stakeholder engagement:
By using Sprint reviews and
Providing timely reports based on their concerns
As our project is an internal project for the company all the expertise are from inside the company
Based on our agile approach, most of the team conflict will be solve internally by communicating team members with each other and if it does not work that way , the Campaign manager and project managers will try to facilitate these kind of conflicts in a good way

## Slide 12: Challenges and Solutions:
Project Management Plan
Project Documents
Project Milestones
Project Schedule
Risk Register
Requirement Gathering
Project Communication
…
Change Request
Change log
Lesson Learned Register
Update
Updated Work Performance
Validate & Control
Scope
Control Cost & Schedule
Control Resources
Control Quality
Monitor Communications
Validate
Scope
Change Request
Issue Log
Notes: The task of controlling and monitoring the progress is assigned to the Campaign manager
Campaign manager is asked to communicate the necessary information based on the RACI matrix and Communication plan to respective parties and stakeholders.
We need to ensure that all related documents such as Project management plan, Schedule , etc., are kept updated according to the change log
Tracks, reviews and regulates the progress and performance of the project and identifies corrective action or changes if needed
Also we Monitor stakeholder Engagement
Monitor & Control Project Work
Perform Integrated Control Change
Validate Scope
  - at the end of any major deliverables
  - We check for the completeness of the deliverables
  for each deliverable this validation performed by PM, Sponsor and related key stakeholders
  We do that in each Sprint review (based on our communication doc)
    In each sprint review the stakeholders Examine and Test the deliverables
Control Scope
After each Scope Validation, we updated “work performance “ , Then in this step we compare it with our baseline
If any changed is required we handle it through Change management process and creating Change request & after approved or reject we update the Change Log document.
Control Schedule
- Iteration burndown chart , we compare our planned backlog with actual results (as our approach is agile)
Control Costs
By using Data Analysis techniques & Earned Value Analysis
We might need some change request in this part
Control Quality
We use check lists for controlling Quality of any deliverables
Also in test campaign steps we will test the performance & quality of our designed campaign
Control Resource
For example In the running part of the campaign there is some risk that our infrastructure could not handle the load of traffics, so there might be some resource & supply damage. In these situations We will define this problem, find the roots of the problem and choose a suitable solution to solve and check if it solve or not.
As we use Agile approach, part of daily meetings will assign to the barriers and obstacle that team is encounter, so the approach is to solve them as soon as possible and before the end of the sprint with minimum effect to the sprint value.
Monitor Communications
-
Monitor Risks
  Identify new risks
  We continuedly monitor for emerging risks and change the status of identified risks
Control Procurements
Monitor Stakeholder Engagements

## Slide 13: Conclusion and Future Work:
Lesson Learned Register
Close Project
Asset Update
Final Report
Finalize Contractual Agreements
Transfer the results to Sale & Customer Service
Releasing Staffs
Releasing Other Resources
Stakeholder Satisfaction measurment
Final Transition
Subcriptions of ads & promotion channels
Project Review
Update Documents
Lesson Learned
Archive info
Notes: These are some of the Final reports that needed to be done in this group:
Main campaign Assessment analytics
Sales report from sales department
Customer care report from customer services
Some examples of Lessons learned in this projects are:
  Objectives were clearly defined and quantified
  We had Flaws in scheduling that we should learn not to repeat
  use of Slack conversation threads was effective int course of the project
For Asset Update:
The time of project staff is freed, and they can return to their day-to-day activities until a new project need arises

## Slide 14: Thanks!
Do you have any questions?