## Slide 1: Student Research Zekelman School of IT (DAB)
DAB-402: Group 12

## Slide 2: Agenda
Who are all involved?
  Team
  Stakeholders
Which area we want to explore?
  Introduction
  Problem Statement
What’s in the Data?
When are we doing it?
  Current Progress
  Overall Timeline
How are we doing it?
  Method and Technology
Where are we heading?
  Challenges
  Further Steps
Questions

## Slide 3: Group #12: Team
Amit Sharma
0794488
Role: Group Leader
Skills: DB Pipelines, Leadership & Cloud
Rajvi Mehta
ID: 0788372
Role: Researcher
Skills: Online Search, Data Collections & Data Work
Suhail Ahmed
Id: 0789949
Role: BI and Data
Skills: Tableau Dashboard Data Engineering & SQL
Jayraj Radadiya
ID: 0789984
Role: Programming & BI
Skills: Python & Dashboards
Harshil Patel
ID: 0791261
Role:
Skills: Tableau, Data
Surveys & Communications
Manjari Maheshwari
Role: Guide and Stakeholder
John Gerassimou
Role: Guide and Data pipeline
3

## Slide 4: Stakeholders
Streamlined and Comprehensive study for understanding student’s data and concerns.
College
Management
Students
Project Team
Benefits
Stakeholders
The main objective is to collect and conduct a detailed and relational analysis/study of data pertaining to all current students enrolled in the DAB program.
Work on a problem and learn various technology platforms and understand Data pipelines
Platform for raising and addressing Student’s concerns regarding Living and Academics
4

## Slide 5: Introduction
The project aims to improve the student experience at St Clair College's Data Analytics for Business program.
The main objective is to create a centralized system for collecting and utilizing student data and monitor their needs and problems.
Goals include identifying key issues and potential solutions through data analysis and presenting findings through an interactive dashboard.
Another goal is to create a template for other departments to use.
Success will be measured through data accuracy, user feedback, adoption rate, user engagement, and trend analysis.
The project will use primary and secondary data sets, machine learning techniques, and tools like Python and Tableau.

## Slide 6: Research Question
St Clair College's Data Analytics for Business program is facing a challenge in effectively analyzing student trends and sentiments
This challenge is due to a lack of a centralized system for collecting and managing student data
The lack of organization is leading to a lack of visibility into student issues
This lack of visibility may result in a lack of satisfaction among students
The project aims to create a centralized system for collecting and utilizing student data
The project also aims to create a mechanism to monitor and understand student needs and their problems
The student needs and problems include challenges related to accommodation, transportation, educational support, the college schedule, health services, and other matters.

## Slide 7: What’s in the Data
Demographic
Ease of living
Academics
1
HOW:
Primary data collection was conducted through surveys.
The collected data is stored in an Excel online file. To automate the transfer of data from Excel to Google Cloud, we used Microsoft Power Automate to connect the data to Google Drive and facilitate the transfer process.
WHY:
To understand student’s opinions, attitudes, and behaviors
To evaluate programs and services
To improve communication and engagement
3
2
WHAT:
Our data collection process consisted of three parts: demographics, ease of living, and academics.
Demographics: collected information about student backgrounds and personal characteristics.
Ease of Living: focused on students' experiences with housing, transportation, and other aspects of student life.
Academics: gathered data on students' academic performance and experiences.
These three parts provided us with a comprehensive overview of students' experiences and feedback.
SURVEY DATA
7

## Slide 8: Progress (till now)
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
STEP 6
STEP 7
STEP 8
Stakeholder
meeting
Problem
Statement
definition
Research & study
Survey setup &
Publishing it
Data
Assessment
Data
Pipeline
ML
Algorithm
Initial
DB
setup

## Slide 9: Timeline plan
Survey 1
Business Problem Formulation
01
January2023
W1
W2
W3
W4
Data
Assessment
Data work
02
February 2023
W1
W2
W3
W4
Dashboard 1
Dashboard Work
03
Survey 2
Survey 2
Work
04
Today
March 2023
W1
W2
W3
W4
Final Report
Data Work
& Pipeline Integration
ML and Dashboard
05
April 2023
W1
W2
W3
W4
Data Collection
Data Pipeline/DB
Machine Learning
06
Final Dashboard
https://github.com/JayrajRadadiya/Capstone-Project/tree/main/ProjectPlan

## Slide 10
Data Intake Phase - Power Automate
Database Ingestion - .CSV to Big Query (through Drive)
Data Movement – DB architecture (inside the Database)
DB to Google Colab (for ML)
Data Stored back to DB
Data to Dashboard (in Tableau)

## Slide 11: Challenges and Solutions
Data Ethics & Collection
As PII Data is involved there is always a challenge
Solution: Used Microsoft Forms to maintain Ethical concerns. No tracking of IDs was allowed as part of survey.
Efforts to advertise the survey through classes and faculty members enabled to obtain more than 60% of the intended data.
Automation
Manual data flow (for the project) has been defined, but we are exploring ways to automate the process for faster results and one click approach despite the current manual access to active components.
Solution: No Solution yet, Still under consideration
Cloud Pipeline
To understand and implement a Data Pipeline which can work being online (cloud based) and act as a repository for the data
Solution: After thorough research we decided to use Google cloud platform and Big-query
Data Engineering
Survey design was intended to be straightforward, but including text field questions has resulted in a data engineering challenges
Solution: Python and SQL Data Cleaning and Standardization

## Slide 12: Further Steps & Plan
Phase 1:
Machine Learning Analysis – Phase 1
Data pipeline extension
Dashboard – Stage 1
Phase 2:
Survey 2 – Data collection
Data Work and Analysis
Dashboard – Stage 2
Final Reporting
Timeline: March 2023 and April 2023

## Slide 13: Questions/ Feedback
13